## Index
Office Move-In — Master Template Workbook
Every tab is a working tool · full guides at office-move-in-guide.vercel.app/tools
• Make it yours: in Google Sheets, File → Make a copy. In Excel, Save As.
• ★ marks the build-first starter set — fifteen tabs that deliver value on day one.
• Gray italic rows are examples — they show the shape; clear them and enter your own.
• Every tab links back here (← Index) and out to its full guide (Guide ↗).
PROJECT CONTROL
★ | Open-Item Tracker | The single list where every loose end lives — with an owner, a due date, a blocker, and a next action — so nothing falls through.
★ | Workstream Owner Matrix | Assign one owner to each of the 14 workstreams so nothing is unowned. The fastest way to stop being the default owner of everything.
★ | 30-Day Critical Path | The whole month on one page — what to do each phase, in the right order, with the output each phase should produce.
★ | Weekly Status Update | A short, repeatable weekly note to leadership. Tells them one thing clearly — is opening day protected, and where do you need help?
| Command Center Setup | The one place your whole move lives. A setup checklist for the single source of truth — what it must contain and who keeps it current.
| Decision Log | A simple record of decisions made — what, who decided, when, and why — so settled questions stay settled and you're not relitigating in week four.
| Risk Register | A short list of what could derail opening day — the risk, how likely, the impact, and your mitigation — reviewed weekly so nothing blindsides you.
| Daily Standup Agenda | The five-question, 15-minute agenda you run every business day until opening, so problems surface while they're still small.
INTAKE & CONTACTS
★ | First 24 Hours Checklist | A do-this-now checklist for your first day. Collect documents, build contacts, confirm dates, define Minimum Viable Opening (MVO), and start the tracker.
★ | Vendor Directory | One contact list for every person who touches the move — internal team, building, and vendors — with roles, backups, and numbers.
BUILDING
★ | Property Manager Intake Questions | The question set to run with your property manager on day one — access, certificates of insurance (COIs), freight elevator, hours, approvals — so nothing blocks the move later.
| Access Request Email | A ready-to-send email that gets your movers and vendors approved for building access — names, dates, COIs, after-hours — before they show up.
| COI Tracker | One place to track every vendor's certificate of insurance — required language, who's named, submitted, approved — so no one gets turned away on move day.
| Freight Elevator Reservation Checklist | The booking checklist for the building's freight elevator and loading dock — windows, dimensions, weight, protection — so deliveries and the move don't wait.
| Building Rules Summary | A one-page summary of the building's rules — access, hours, insurance, freight, protection, approvals — captured from your property manager (PM) so the whole team works from the same facts.
CONSTRUCTION
★ | Punch List | One list for every unfinished or fix-it item, with a photo and an owner, so nothing gets lost between "almost done" and "done."
| Scope Snapshot | A one-page snapshot of the build-out — what's in scope, who's doing it, and what's opening-critical vs. finish work — so you know what "done" means.
| Site Walk Checklist | What to look at on every site walk — power, paths, doors, rooms, life safety — so each visit updates the punch list instead of being a stroll.
| Photo Log | A simple photo record of conditions and progress — dated, located, and tied to punch items — so "what did it look like then?" always has an answer.
| Scope Change Log | A short form to capture any change to the build-out — what changed, why, cost, schedule impact, who approved — so scope creep doesn't quietly blow your budget or date.
FF&E
★ | FF&E Inventory | A running inventory of furniture, fixtures, and equipment — what exists, what's ordered, what's missing, and whether it'll be there in time.
| Furniture Order Tracker | Every furniture order in one view — what's ordered, approved, paid, and when it lands — so nothing's "assumed handled" while a lead time quietly eats your timeline.
| Delivery & Install Schedule | A dated schedule for every delivery and install — sequenced against freight windows and power readiness — so furniture arrives when the space can actually receive it.
| Damage & Warranty Log | Document damaged or missing items the moment they're found, with photos and claim status — because undocumented damage at install becomes your problem later.
| Reuse / Donate / Recycle Tracker | A disposition plan for furniture you're not keeping — reuse, donate, liquidate, or recycle — so the old space (and the new one's overflow) doesn't become a forgotten cost.
IT / AV
★ | IT/AV Readiness Checklist | Test everything an employee will touch — Wi-Fi, conference rooms, printing, access — before opening day. "Installed" is not "working."
| Conference Room Test Script | A step-by-step test for each meeting room — join, share, camera, audio, booking — because "installed" is not the same as "working."
| Access Card Tracker | Track who has building and suite access — credentials issued, active, and returned — so nobody's stuck in the lobby on day one.
| Security System Checklist | The security setup to confirm before opening — alarms, cameras, after-hours access, the lost-badge process — so the suite is actually secure on night one.
| Opening-Day Tech Support Plan | Who's covering tech on opening morning, how people report problems, and the triage order — so a Wi-Fi hiccup doesn't become the story of day one.
KITCHEN
★ | Kitchen Startup Order List | Everything to buy so the kitchen works on day one — dishware, coffee, water, consumables, cleaning, and a plan to restock.
| Pantry Inventory Tracker | A running list of pantry and kitchen supplies with par levels — so you can see what's low at a glance and the office never quietly runs dry.
| Reorder Cadence | The simple restock plan — who checks, how often, the reorder threshold, who approves — so supplies stay stocked without anyone playing hero.
| Opening-Day Hospitality Checklist | The small touches that make opening day feel hosted — coffee on, snacks out, signage up, kitchen stocked — so people feel welcomed, not just relocated.
MOVE
★ | Move Day Run of Show | One plan for move day — roles, timeline, and a contact tree — so everyone on site knows where to go, who's in charge, and what to do if something changes.
| Move Vendor Scope | The full list to confirm with your moving company in writing — dates, dock, certificate of insurance (COI), protection, labeling, debris — so move day runs on one plan, not a pile of assumptions.
| Packing & Labeling Guide | A simple labeling system so boxes and furniture land in the right room — and nothing gets lost between the old space and the new one.
| Day-Of Contact Tree | The short list of who's in charge on move day — workplace lead, building contact, mover foreman, IT lead, comms, escalation — with phone numbers, on one page.
| Move Completion Checklist | The end-of-move walkthrough — everything delivered, placed, and undamaged — so you sign off the mover knowing nothing's missing or broken.
COMMS
★ | Opening Readiness Checklist | The day-before and opening-morning walk-through. Confirm the office clears the Minimum Viable Opening bar before anyone arrives.
★ | Employee Pre-Move Email | A ready-to-adapt email that tells employees how to arrive successfully — and names what's still in progress so unfinished work doesn't read as chaos.
| Office FAQ | The questions employees will ask on day one — where do I sit, how do I get in, what's the Wi-Fi — answered once, so you're not fielding the same message fifty times.
| Seating Plan Worksheet | A simple worksheet to assign seats before move day — names to desks, teams grouped, special needs handled — so people walk in and find their spot.
FINANCE
| Budget Tracker | Track spend against budget by workstream — committed, paid, and remaining — so you always know what's left before the next urgent order lands.
| Purchase Approval Log | Every purchase tracked through approval and payment — quote, approved amount, PO, deposit, invoice, fees — so nothing stalls for lack of a sign-off.
| Vendor Contract Tracker | A register of vendor contracts and SOWs — scope, term, key dates, deposit, status — so you know what each vendor owes you and when.
| Invoice Checklist | A quick check before paying any invoice — matches the quote/PO, work delivered, fees expected, certificate of insurance (COI) current — so you're not paying for what didn't arrive.
COMPLIANCE
| Safety & Compliance Checklist | The unglamorous opening basics — certificates of insurance (COIs), life safety, evacuation routes, first aid, accessibility, inspections — confirmed before people arrive.
| Emergency Contact Sheet | One sheet of who to call when something goes wrong — building, security, medical, utilities, key vendors — posted where people can find it.
| Final Readiness Walk | The last walk before opening — safety, access, core function, cleanliness — with photos, so you open knowing the space is actually ready.
HYPERCARE & CLOSEOUT
★ | Hypercare Tracker | One issue list for opening week, sorted by urgency, so people can see that someone is watching and fixing the list.
| Issue Intake Form | A simple intake so opening-week issues arrive in one place with what's needed to act — location, problem, reporter, urgency — instead of scattered across channels.
| Week-One Closeout Update | The end-of-first-week update — what opened, what's resolved, what remains and who owns it — that hands the office off from launch mode to normal operations.
| Closeout Binder Checklist | Everything future-you needs in one place — floor plan, vendor directory, warranties, manuals, access records, budget archive, lessons learned.
| Recurring Operations Calendar | The schedule that keeps the office running after opening — janitorial, restock, HVAC, pest, plants, walk-throughs — so operations run on a cadence, not on memory.
| Vendor Performance Notes | A quick record of how each vendor actually performed — on time, on budget, would-rehire — so renewals and the next project start from evidence, not memory.
| Lessons Learned Log | What worked, what didn't, and what you'd tell the next person — captured while it's fresh, so the next opening (or the next hire) starts smarter.
GREAT WORKPLACE
| Great-Office Scorecard | A ten-minute self-assessment of your office against the six-pillar standard — to find the weakest pillar and your next improvement.
| Space & Ratios Worksheet | Size the mix — desks, meeting rooms, focus and social space — against your real headcount and in-office pattern, before you lock the layout.
| Workplace Experience Survey | A short, recurring pulse on how the office actually feels to the people in it — across the six pillars. Two minutes to answer, honest signal back.
| Post-Occupancy Review | A structured look back at 30 / 60 / 90 days after opening — what's working, what isn't, and what to fix while impressions are fresh.
| Quarterly Workplace Review | The recurring home for "keep it great" — revisit the signals, pick one pillar, ship one improvement. The cadence that stops an office from drifting.
| Day-One Greatness Checklist | Beyond the opening-readiness floor — did we actually open great? A six-pillar check for opening morning, not just "is it safe to use?"

## Open-Item Tracker
Open-Item Tracker | [6 empty] | ← Index
The single list where every loose end lives — with an owner, a due date, a blocker, and a next action — so nothing falls through. | [6 empty] | Guide ↗
Workstream | Item | Owner | Due date | Status | Blocker | Next action | Decision needed
Building | Submit mover COI to PM | A. Lee | 2026-06-06 | In progress | Need mover's insurer info | Email mover for COI today | —
IT/AV | Confirm internet circuit live date | J. Park | 2026-06-09 | Blocked | ISP hasn't confirmed | Escalate to ISP rep | Approve rush fee?
FF&E | Reserve freight elevator for install | A. Lee | 2026-06-05 | Not started | — | Call PM to book window | —

## Workstream Owner Matrix
Workstream Owner Matrix |  |  |  |  | ← Index
Assign one owner to each of the 14 workstreams so nothing is unowned. The fastest way to stop being the default owner of everything. |  |  |  |  | Guide ↗
# | Workstream | Typical owner | Owner | Backup | Status / notes
1 | Project Control & Governance | Workplace lead / PM
2 | Property Manager & Building Rules | Workplace lead / PM / facilities
3 | Construction, Light TI & Punch | PM / GC / workplace lead
4 | Furniture, Fixtures & Equipment (FF&E) | Workplace lead / dealer
5 | IT, Network, AV & Conference Rooms | IT lead / AV vendor
6 | Access Control, Security & Visitors | Workplace lead / IT-security / PM
7 | Move Logistics | Workplace lead / mover
8 | Kitchen, Pantry & Hospitality | Workplace lead / office manager
9 | Office Supplies, Mail, Print & Storage | Workplace lead / office manager
10 | Janitorial, Trash, Plants, Pest & Facilities | Workplace lead / PM / facilities
11 | Employee Comms & Opening Experience | Workplace lead / People / comms
12 | Finance, Procurement & Budget | Workplace lead / finance
13 | Compliance, Insurance, Health & Safety | Workplace lead / People / legal / PM
14 | Decommissioning & Old-Space Closeout | Workplace lead / mover / vendor

## 30-Day Critical Path
30-Day Critical Path |  |  |  |  | ← Index
The whole month on one page — what to do each phase, in the right order, with the output each phase should produce. |  |  |  |  | Guide ↗
Done | Days | Phase | Goal | Key actions | Output (you are not done without this)
| Days 1–2 | Stabilize | Understand reality and create control. | Collect documents · build contact list · confirm move-in + access dates · meet/email the property manager · identify all vendors · define Minimum Viable Opening · build the open-item tracker · identify blockers · set the daily standup · schedule vendor check-ins. | command center · contact list · critical path · initial risk list.
| Days 3–5 | Lock the Opening Plan | Remove preventable blockers. | Submit certificates of insurance (COIs) and access-request forms · reserve freight elevator / loading dock · confirm after-hours rules · confirm vendor start dates · confirm furniture delivery/install · confirm internet/network readiness · confirm conference-room/audio/visual (AV) path · place kitchen, pantry, supply, and cleaning orders · confirm janitorial scope · draft the employee pre-move communication. | opening plan · vendor schedule · building-approvals tracker · purchase tracker.
| Week 2 | Build the Backbone | Make the space functional. | Complete electrical/power · confirm network/Wi-Fi · coordinate IT/AV install · confirm furniture logistics · start access-card/badge process · resolve building-approval issues · walk the space and update the punch list · confirm move-vendor scope · confirm kitchen/pantry delivery timing. | functional readiness check · updated punch list · confirmed move-day run of show.
| Week 3 | Assemble the Office | Turn the space into a usable workplace. | Receive and install furniture · test desks, power, monitors, rooms, Wi-Fi, AV, access · stock kitchen and office supplies · set up mail/shipping · label storage and supply areas · finalize seating · send the employee pre-move email · schedule the final clean · hold the day-before readiness meeting. | opening readiness checklist · employee instructions · support plan.
| Week 4 | Move, Open, and Support | Move in without chaos, then manage the first wave of issues. | Run move day from a command center · keep one issue tracker · staff opening morning · test rooms and Wi-Fi before employees arrive · post temporary signage · watch kitchen/restroom/supply areas · triage issues (urgent / opening-week / post-opening / nice-to-have) · send daily updates if visible work remains · close the week with a leadership update. | hypercare tracker · punch list by owner · week-one closeout update.

## Weekly Status Update
Weekly Status Update | ← Index
A short, repeatable weekly note to leadership. Tells them one thing clearly — is opening day protected, and where do you need help? | Guide ↗
Section | Your update
Week of
Overall status
Opening date
Confidence
Confidence — because (one line)
Completed this week
In progress
Blocked / at risk — item · why · what would unblock it
Decisions needed — decision · needed by · options
Next 7 days

## Command Center Setup
Command Center Setup |  |  |  | ← Index
The one place your whole move lives. A setup checklist for the single source of truth — what it must contain and who keeps it current. |  |  |  | Guide ↗
Done | Item | Owner | Due | Notes
☐ | Critical path — the dated plan
☐ | Minimum Viable Opening definition
☐ | Contacts — internal team and decision-makers
☐ | Vendor Directory
☐ | Open-Item Tracker
☐ | Building requests — certificates of insurance (COIs) / access (COI Tracker)
☐ | Punch list
☐ | Purchases / budget
☐ | Employee communications
☐ | Hypercare Tracker (ready for opening week)

## Decision Log
Decision Log |  |  |  |  | ← Index
A simple record of decisions made — what, who decided, when, and why — so settled questions stay settled and you're not relitigating in week four. |  |  |  |  | Guide ↗
Date | Decision | Made by | Why / context | Affects | Revisit?
2026-06-04 | Open with 6 of 8 conference rooms; finish 2 post-opening | Workplace lead + Ops | AV for 2 rooms slips past opening; not opening-critical | IT/AV, Comms | No
2026-06-05 | Reuse existing desks, buy new chairs only | Finance | Budget; desks are fine, chairs aren't | FF&E, Finance | No
2026-06-06 | Approve rush fee to pull internet install forward | Founder | Connectivity is opening-critical | IT/AV | No

## Risk Register
Risk Register |  |  |  |  | ← Index
A short list of what could derail opening day — the risk, how likely, the impact, and your mitigation — reviewed weekly so nothing blindsides you. |  |  |  |  | Guide ↗
Risk | Likelihood | Impact | Owner | Mitigation / next action | Status
Internet circuit not live by opening | Medium | High | J. Park | Confirm install date; line up hotspots as backup | Watching
Conference table won't fit freight elevator | Low | High | A. Lee | Measure vs. elevator this week | Watching
Furniture install slips | Medium | Medium | A. Lee | Confirm delivery date; hold install crew | Mitigated

## Daily Standup Agenda
Daily Standup Agenda |  |  | ← Index
The five-question, 15-minute agenda you run every business day until opening, so problems surface while they're still small. |  |  | Guide ↗
# | Question | Where it goes / what to capture | Today's notes
1 | What changed since yesterday? | New facts only — not a recap
2 | What's blocked? | Spend the time here; every blocker leaves with an owner + next action
3 | What must happen today? | Today's must-dos, off the Open-Item Tracker
4 | What decisions are needed? | Route to the Decision Log
5 | What needs escalation? | Route to the Weekly Status Update

## First 24 Hours Checklist
First 24 Hours Checklist |  |  |  | ← Index
A do-this-now checklist for your first day. Collect documents, build contacts, confirm dates, define Minimum Viable Opening (MVO), and start the tracker. |  |  |  | Guide ↗
Done | Item | Owner | Due | Notes
☐ | Signed lease or sublease
☐ | Work letter / tenant-improvement exhibit
☐ | Building rules and regulations
☐ | Building moving policy
☐ | Insurance requirements — the certificate of insurance (COI) language the building requires
☐ | Approved drawings or furniture plans
☐ | Scopes of work from the general contractor (GC), designer, audio/visual (AV), IT, and furniture vendors
☐ | Furniture inventory
☐ | Vendor quotes and open proposals
☐ | Property-manager correspondence
☐ | Any pending approval requests
☐ | Current move date / target opening date

## Vendor Directory
Vendor Directory | [6 empty] | ← Index
One contact list for every person who touches the move — internal team, building, and vendors — with roles, backups, and numbers. | [6 empty] | Guide ↗
Role | Company | Primary contact | Email | Phone | Backup | Workstream | Notes
Property manager | — | — | — | — | — | Building | Approves vendor access
Mover (foreman) | — | — | — | — | — | Move | Confirm day-of cell
IT lead | — | — | — | — | — | IT/AV | On site opening AM

## PM Intake Questions
Property Manager Intake Questions |  |  |  | ← Index
The question set to run with your property manager on day one — access, certificates of insurance (COIs), freight elevator, hours, approvals — so nothing blocks the move later. |  |  |  | Guide ↗
Done | Item | Owner | Due | Notes
☐ | Who approves vendor access, and how far ahead must requests go in?
☐ | What forms are required for movers, vendors, and after-hours work?
☐ | How are employee access cards or mobile credentials issued?
☐ | What's the building emergency contact?

## Access Request Email
Access Request Email | ← Index
A ready-to-send email that gets your movers and vendors approved for building access — names, dates, COIs, after-hours — before they show up. | Guide ↗
Part | Email text — fill the [brackets], cut what does not apply
Subject | Access request — [Your Company], Suite [###] — [date(s)]
Body | Hi [Property Manager name], We're preparing for [our move-in / a vendor visit] and would like to request building access. Details:
• | Company / vendor: [vendor name]
• | On-site contact: [name, mobile]
• | Date(s) and time(s): [e.g., Sat Jun 14, 7am–3pm] — please confirm this is within allowed hours
• | Work being done: [e.g., furniture delivery and install]
• | Crew size / vehicles: [e.g., 6 people, one 26ft truck]
• | Freight elevator / loading dock: we'd like to reserve [window] — please advise on availability and any size/weight limits
• | COI: attached / being submitted separately to [email]; please confirm it meets requirements
Body | Could you let me know what else you need from us, and confirm the request once approved? Happy to fill out any building forms — just point me to them. Thanks so much, [Your name] · [Your Company] · [phone]

## COI Tracker
COI Tracker | [7 empty] | ← Index
One place to track every vendor's certificate of insurance — required language, who's named, submitted, approved — so no one gets turned away on move day. | [7 empty] | Guide ↗
Vendor | Work | COI requested | Language sent | Additional insured correct | Submitted to PM | PM approved | Expiry | Status
ABC Movers | Move day | Jun 2 | Yes | Yes | Jun 4 | ✓ Jun 6 | Dec 2026 | Done
Acme Furniture | Delivery/install | Jun 2 | Yes | Pending | — | — | — | In progress
NetWire IT | Cabling | Jun 3 | Yes | Yes | Jun 5 | Awaiting | Aug 2026 | Blocked

## Freight Elevator Booking
Freight Elevator Reservation Checklist |  |  |  | ← Index
The booking checklist for the building's freight elevator and loading dock — windows, dimensions, weight, protection — so deliveries and the move don't wait. |  |  |  | Guide ↗
Done | Item | Owner | Due | Notes
☐ | Freight elevator reserved for furniture delivery/install date
☐ | Freight elevator reserved for move day
☐ | Loading dock reserved for the same windows
☐ | After-hours/weekend use approved (if needed) and any fees confirmed

## Building Rules Summary
Building Rules Summary |  |  | ← Index
A one-page summary of the building's rules — access, hours, insurance, freight, protection, approvals — captured from your property manager (PM) so the whole team works from the same facts. |  |  | Guide ↗
Rule | This building's answer | What to capture | Confirmed (date)
Work hours |  | When work is allowed (weekday/after-hours/weekend)
Move hours |  | When moves are allowed
Vendor access |  | Who approves it; lead time; access form needed
Employee access |  | How cards / mobile credentials are issued
Insurance |  | Required COI language; who's named additional insured; where to submit
Freight elevator |  | How to reserve; windows; dimensions; weight limit
Loading dock |  | Hours; truck size limit; booking process
Protection |  | Floor/wall protection required; who supplies it
Debris |  | Can vendors use building trash, or must they haul away?
HVAC |  | Standard hours; how to request after-hours
Labor |  | Is union labor required for any work?
Approvals |  | Permits, stamped drawings, inspections, landlord sign-offs needed
Contacts |  | Property manager; building security; emergency number

## Punch List
Punch List | [6 empty] | ← Index
One list for every unfinished or fix-it item, with a photo and an owner, so nothing gets lost between "almost done" and "done." | [6 empty] | Guide ↗
# | Location | Description | Photo | Owner | Priority | Due date | Status
1 | Room 2 (NE corner) | Outlet not powered at desk run | [link] | GC | Opening-critical | 2026-06-12 | Open
2 | Reception | Wall paint scuffed near door | [link] | GC | Post-opening | 2026-06-26 | Open
3 | Kitchen | Cabinet door misaligned | [link] | GC | Nice-to-have | — | Open

## Scope Snapshot
Scope Snapshot |  |  |  | ← Index
A one-page snapshot of the build-out — what's in scope, who's doing it, and what's opening-critical vs. finish work — so you know what "done" means. |  |  |  | Guide ↗
Scope item | Owner | Opening-critical? | Status | Notes
Power to all workstations | GC | Yes | In progress | Pacing the desk install
Demising wall paint | GC | No | Not started | Post-opening
Conference room A/V rough-in | AV vendor | Yes (day-one rooms) | In progress | —
Accent lighting | GC | No | Not started | Finish work

## Site Walk Checklist
Site Walk Checklist |  |  |  | ← Index
What to look at on every site walk — power, paths, doors, rooms, life safety — so each visit updates the punch list instead of being a stroll. |  |  |  | Guide ↗
Done | Item | Owner | Due | Notes
☐ | Power — outlets live where desks will go; panel work progressing
☐ | Paths of travel — clear, safe, no trip hazards or blocked exits
☐ | Doors, locks, access — suite entry and interior doors function
☐ | Restrooms & kitchen — plumbing and fixtures working
☐ | Day-one conference rooms — ready for audio/visual (AV) and use
☐ | Floors & walls — conditions that affect safety or install
☐ | Life safety — exit signs, extinguishers, alarms present
☐ | Lighting & HVAC — on and functioning in occupied areas
☐ | Required approvals/inspections — visibly on track

## Photo Log
Photo Log |  |  |  | ← Index
A simple photo record of conditions and progress — dated, located, and tied to punch items — so "what did it look like then?" always has an answer. |  |  |  | Guide ↗
Date | Location | What it shows | Linked item | Photo
2026-06-10 | Suite entry | Pre-existing scratch on door | Punch #4 | ✓
2026-06-16 | Open area B | Power installed at desks | Scope: power | ✓
2026-06-17 | Conf. Room A | Chipped table on delivery | Damage log #2 | ✓

## Scope Change Log
Scope Change Log | [7 empty] | ← Index
A short form to capture any change to the build-out — what changed, why, cost, schedule impact, who approved — so scope creep doesn't quietly blow your budget or date. | [7 empty] | Guide ↗
Date | Change requested | Reason | Cost impact ($) | Schedule impact (days) | Opening-critical? | Requested by | Approved by | Status
2026-06-11 | Add two power poles in open area | Desk layout moved off the wall | 2400 | 0 | No | A. Lee | P. Ortiz · Jun 12 | Approved

## FF&E Inventory
FF&E Inventory | [6 empty] | ← Index
A running inventory of furniture, fixtures, and equipment — what exists, what's ordered, what's missing, and whether it'll be there in time. | [6 empty] | Guide ↗
Item | Qty needed | Have / ordered / missing | Owner | Delivery date | Install date | Freight reserved? | Status / notes
Sit/stand desks | 40 | Ordered | Dealer | 2026-06-14 | 2026-06-15 | Yes | Confirm power aligns
Task chairs | 40 | Ordered | Dealer | 2026-06-14 | — | Yes | —
Conf. room table (Rm 1) | 1 | Have | — | — | — | — | Reuse from old space
Monitors + arms | 40 | Missing | IT | — | — | — | Not yet ordered — risk

## Furniture Order Tracker
Furniture Order Tracker | [6 empty] | ← Index
Every furniture order in one view — what's ordered, approved, paid, and when it lands — so nothing's "assumed handled" while a lead time quietly eats your timeline. | [6 empty] | Guide ↗
Item | Vendor | Qty | Status | Approved by | Lead time | Expected delivery | Notes
Task chairs | Acme | 60 | Ordered | Finance | 6 wks | 2026-06-18 | Confirmed
Sit/stand desks | Acme | 60 | Approved | Finance | 8 wks | — | Place order today
Conf. tables (x4) | Workspace Co | 4 | Quoted | — | 10 wks | — | Long lead — decide now

## Delivery & Install Schedule
Delivery & Install Schedule | [5 empty] | ← Index
A dated schedule for every delivery and install — sequenced against freight windows and power readiness — so furniture arrives when the space can actually receive it. | [5 empty] | Guide ↗
Date | Item / vendor | Type | Freight booked? | Receiver | Dependencies ready? | Status
2026-06-16 | Desks / Acme | Install | Yes | A. Lee | Power at desks ✓ | Confirmed
2026-06-17 | Chairs / Acme | Delivery | Yes | A. Lee | — | Confirmed
2026-06-18 | Conf. tables / Workspace | Install | Pending | A. Lee | AV rough-in ✓ | At risk

## Damage & Warranty Log
Damage & Warranty Log | [5 empty] | ← Index
Document damaged or missing items the moment they're found, with photos and claim status — because undocumented damage at install becomes your problem later. | [5 empty] | Guide ↗
Item | Found (when / where) | Photo | Issue | Vendor | Claim / RMA # | Status
Task chair #14 | Jun 17, install | ✓ | Torn armrest | Acme | RMA-2231 | Replacement shipped
Conf. table | Jun 18, delivery | ✓ | Scratched top | Workspace Co | CL-0094 | Filed
Monitor arm | Jun 17, install | ✓ | Missing from box | Acme | — | Reordering

## Reuse-Donate-Recycle
Reuse / Donate / Recycle Tracker |  |  |  |  | ← Index
A disposition plan for furniture you're not keeping — reuse, donate, liquidate, or recycle — so the old space (and the new one's overflow) doesn't become a forgotten cost. |  |  |  |  | Guide ↗
Item | Qty | Disposition | Recipient / vendor | Pickup date | Status
Old desks | 24 | Donate | Local nonprofit | 2026-06-20 | Scheduled
Surplus chairs | 18 | Liquidate | Used-office dealer | 2026-06-21 | Quote in
Broken storage | 6 | Recycle | Hauler | 2026-06-22 | Booked
Lounge sofa | 1 | Reuse (new space) | — | — | Moving

## IT-AV Readiness Checklist
IT/AV Readiness Checklist |  |  |  | ← Index
Test everything an employee will touch — Wi-Fi, conference rooms, printing, access — before opening day. "Installed" is not "working." |  |  |  | Guide ↗
Done | Item | Owner | Due | Notes
☐ | Wi-Fi (and guest Wi-Fi, if used)
☐ | Wired network (if used)
☐ | Internet circuit confirmed live (not just "ordered")
☐ | Video call from each priority room — camera, microphone, speakers, screen share
☐ | Room booking display (if used)
☐ | Printers / scanners (if used) — networked, not just plugged in
☐ | Access cards / mobile credentials
☐ | Visitor check-in (if used)

## Conference Room Test Script
Conference Room Test Script |  |  |  | ← Index
A step-by-step test for each meeting room — join, share, camera, audio, booking — because "installed" is not the same as "working." |  |  |  | Guide ↗
Done | Item | Owner | Due | Notes
☐ | 1. Join a video call from the room system
☐ | 2. Invite someone remote to join
☐ | 3. Confirm the remote person can hear the room
☐ | 4. Confirm the room can hear the remote person
☐ | 5. Share a screen
☐ | 6. Check camera framing
☐ | 7. Test room booking (panel/calendar), if used
☐ | 8. Confirm the how-to is visible or obvious for a first-time user

## Access Card Tracker
Access Card Tracker | [5 empty] | ← Index
Track who has building and suite access — credentials issued, active, and returned — so nobody's stuck in the lobby on day one. | [5 empty] | Guide ↗
Person / group | Building access | Suite access | After-hours | Credential issued | Active | Returned
All employees | Card | Card | No | Jun 12 | ✓ | —
Workplace lead | Card | Card | Yes | Jun 10 | ✓ | —
Cleaning vendor | Building | Suite (after-hours) | Yes | Jun 13 | Pending | —

## Security System Checklist
Security System Checklist |  |  |  | ← Index
The security setup to confirm before opening — alarms, cameras, after-hours access, the lost-badge process — so the suite is actually secure on night one. |  |  |  | Guide ↗
Done | Item | Owner | Due | Notes
☐ | Employee credentials issued and active (Access Card Tracker)
☐ | Vendor access process defined
☐ | After-hours access working for those who need it
☐ | Suite keys accounted for (if applicable)
☐ | Lost / replacement badge process documented

## Opening-Day Tech Support
Opening-Day Tech Support Plan |  |  |  | ← Index
Who's covering tech on opening morning, how people report problems, and the triage order — so a Wi-Fi hiccup doesn't become the story of day one. |  |  |  | Guide ↗
Done | Item | Owner | Due | Notes
☐ | On-site IT support staffed for opening morning (or remote contact named + reachable)
☐ | Backup contact if the primary is pulled away
☐ | Audio/visual (AV)/room support owner identified (Conference Room Test Script)

## Kitchen Startup Order List
Kitchen Startup Order List |  |  |  | ← Index
Everything to buy so the kitchen works on day one — dishware, coffee, water, consumables, cleaning, and a plan to restock. |  |  |  | Guide ↗
Done | Item | Owner | Due | Notes
☐ | Who checks inventory, and how often?
☐ | Where are backup supplies stored?
☐ | What's the reorder threshold (reorder when down to ___)?
☐ | Who approves purchases?
☐ | What vendor or platform do we use?

## Pantry Inventory Tracker
Pantry Inventory Tracker |  |  |  |  | ← Index
A running list of pantry and kitchen supplies with par levels — so you can see what's low at a glance and the office never quietly runs dry. |  |  |  |  | Guide ↗
Item | Category | Par level | On hand | Reorder? | Vendor
Coffee | Coffee/tea | 4 bags | 1 | Yes | Vendor
Paper towels | Consumables | 6 rolls | 5 | Yes | —
Dish soap | Cleaning | 2 | 0 | Yes | —
Trash bags | Consumables | 1 box | 1 | Yes | —

## Reorder Cadence
Reorder Cadence |  |  |  | ← Index
The simple restock plan — who checks, how often, the reorder threshold, who approves — so supplies stay stocked without anyone playing hero. |  |  |  | Guide ↗
Done | Item | Owner | Due | Notes
☐ | Who checks inventory? One named person.
☐ | How often? A set day (e.g., every Monday).
☐ | Where are backups stored? One known location.
☐ | What's the reorder threshold? The par levels in your Pantry Inventory Tracker.
☐ | Who approves purchases, and via what vendor/platform? One approver, one ordering path.

## Opening-Day Hospitality
Opening-Day Hospitality Checklist |  |  |  | ← Index
The small touches that make opening day feel hosted — coffee on, snacks out, signage up, kitchen stocked — so people feel welcomed, not just relocated. |  |  |  | Guide ↗
Done | Item | Owner | Due | Notes
☐ | Coffee and tea brewing / ready
☐ | Water dispenser working, cups out
☐ | Snacks and/or fruit set out
☐ | Kitchen stocked and tidy (startup order received)
☐ | Trash and recycling bins out, with liners
☐ | Soap, paper towels, napkins stocked
☐ | First-day catering confirmed (if doing it)

## Move Day Run of Show
Move Day Run of Show |  |  |  | ← Index
One plan for move day — roles, timeline, and a contact tree — so everyone on site knows where to go, who's in charge, and what to do if something changes. |  |  |  | Guide ↗
Done | Item | Owner | Due | Notes
☐ | Date and time · origin and destination
☐ | Loading dock and freight elevator reserved
☐ | certificate of insurance (COI) submitted and approved by the building
☐ | Foreman name + cell · crew size
☐ | Floor and wall protection (who supplies it)
☐ | Packing / crates · labeling system
☐ | Trash / debris removal
☐ | Furniture assembly / disassembly
☐ | IT equipment handling
☐ | Insurance / damage process
☐ | Completion confirmation / sign-off

## Move Vendor Scope
Move Vendor Scope |  |  |  | ← Index
The full list to confirm with your moving company in writing — dates, dock, certificate of insurance (COI), protection, labeling, debris — so move day runs on one plan, not a pile of assumptions. |  |  |  | Guide ↗
Done | Item | Owner | Due | Notes
☐ | Date and time
☐ | Origin and destination addresses
☐ | Loading dock booked
☐ | Freight elevator window booked
☐ | Crew size and foreman contact

## Packing & Labeling Guide
Packing & Labeling Guide |  |  |  | ← Index
A simple labeling system so boxes and furniture land in the right room — and nothing gets lost between the old space and the new one. |  |  |  | Guide ↗
Done | Item | Owner | Due | Notes
☐ | Destination zone + room (e.g., D-3)
☐ | Contents in plain words ("Room 3 — cables, remotes")
☐ | Priority: Day-one or Unpack later
☐ | Owner, if it's someone's personal items

## Day-Of Contact Tree
Day-Of Contact Tree |  |  | ← Index
The short list of who's in charge on move day — workplace lead, building contact, mover foreman, IT lead, comms, escalation — with phone numbers, on one page. |  |  | Guide ↗
Role | Owns | Name | Mobile
Workplace lead | The overall day; final word on the floor
Building contact | Dock, freight elevator, access, building issues
Mover foreman | The crew and the physical move
IT lead | Network, devices, reconnection
Comms owner | Updates to employees / leadership
Escalation decision-maker | Money/scope calls when plans change

## Move Completion Checklist
Move Completion Checklist |  |  |  | ← Index
The end-of-move walkthrough — everything delivered, placed, and undamaged — so you sign off the mover knowing nothing's missing or broken. |  |  |  | Guide ↗
Done | Item | Owner | Due | Notes
☐ | All items delivered (count against the inventory / furniture order)
☐ | Nothing left on the truck, dock, or staging area
☐ | Personal/boxed items reached their labeled destinations

## Opening Readiness Checklist
Opening Readiness Checklist |  |  |  | ← Index
The day-before and opening-morning walk-through. Confirm the office clears the Minimum Viable Opening bar before anyone arrives. |  |  |  | Guide ↗
Done | Item | Owner | Due | Notes
☐ | Walk the full space
☐ | Building access works (badge from the street/lobby)
☐ | Suite access works
☐ | Wi-Fi tested and working
☐ | Priority conference rooms tested on a real call (see IT/AV checklist)
☐ | Restrooms checked (stocked, clean, working)
☐ | Kitchen checked (coffee, water, trash, basics — see kitchen list)
☐ | Trash / recycling in place
☐ | Temporary signage / wayfinding posted
☐ | Seating areas ready; seats findable
☐ | IT support coverage confirmed for the morning
☐ | Issue-reporting channel is live and announced

## Employee Pre-Move Email
Employee Pre-Move Email | ← Index
A ready-to-adapt email that tells employees how to arrive successfully — and names what's still in progress so unfinished work doesn't read as chaos. | Guide ↗
Part | Email text — fill the [brackets], cut what does not apply
Subject | Our new office opens [date] — here's how to arrive
Body | Hi team, We're opening the new office at [address] on [date]. Here's everything you need for a smooth first morning.
Section head | Getting in
• | Arrive at [entrance / floor]. [Building access: badge / front desk / temporary pass.]
• | [Parking / transit notes, if relevant.]
Section head | Finding your spot
• | [Seating: assigned / neighborhoods / pick-a-desk]. [Where to find your seat / map link.]
• | Wi-Fi: [network], password […] (or "credentials will be at your desk").
Section head | What's ready on day one
• | Powered desks, Wi-Fi, [#] meeting rooms, restrooms, kitchen with coffee/water/snacks, and supplies.
Section head | What's still in progress
• | [e.g., artwork, plants, a couple of lounge areas, final signage] — coming over the next [timeframe].
Section head | If something's not right
• | Report it in [channel] and we'll track and fix it. [Who to contact for anything urgent.]
Section head | A few notes
• | [Coffee / breakfast / opening-day welcome details, if any.]
Body | Can't wait to see you there. — [Name]

## Office FAQ
Office FAQ |  |  | ← Index
The questions employees will ask on day one — where do I sit, how do I get in, what's the Wi-Fi — answered once, so you're not fielding the same message fifty times. |  |  | Guide ↗
Question | Your answer | What to cover | Ready?
Where is the office? |  | Address, floor, entrance to use.
How do I get in? |  | Building access, suite access, what to do day one.
Where do I sit? |  | Seating plan / how to find your desk (Seating Plan Worksheet).
What's the Wi-Fi? |  | Network name and how to connect; guest Wi-Fi for visitors.
How do I book / use a meeting room? |  | Day-one rooms and how to start a call.
What's ready, what's not? |  | What works now; what's finishing post-opening.
Food & coffee? |  | What's stocked; kitchen basics.
Guests / deliveries / mail? |  | Visitor check-in and where things arrive.
How do I report a problem? |  | The one support channel — and who to contact.

## Seating Plan Worksheet
Seating Plan Worksheet |  |  |  | ← Index
A simple worksheet to assign seats before move day — names to desks, teams grouped, special needs handled — so people walk in and find their spot. |  |  |  | Guide ↗
Zone / desk | Person | Team | Equipment needed | Notes
B-01 | J. Park | Eng | 2 monitors | —
B-02 | A. Rao | Eng | 1 monitor | —
D-05 | M. Diaz | Sales | Standing desk | Near window (accessibility)

## Budget Tracker
Budget Tracker |  |  |  |  | ← Index
Track spend against budget by workstream — committed, paid, and remaining — so you always know what's left before the next urgent order lands. |  |  |  |  | Guide ↗
Workstream | Budget | Committed | Paid | Remaining | Notes
FF&E | 80000 | 74200 | 30000 | 5800 | Tight — chairs still open
IT/AV | 40000 | 36500 | 20000 | 3500 | Rush fee added
Kitchen | 6000 | 4100 | 4100 | 1900 | —
Move | 18000 | 18000 | 0 | 0 | Invoice due post-move
Total | 144000 | 132800 | 54100 | 11200
Note on E4: Remaining = Budget − Committed. Paid is informational (a subset of Committed).

## Purchase Approval Log
Purchase Approval Log | [7 empty] | ← Index
Every purchase tracked through approval and payment — quote, approved amount, PO, deposit, invoice, fees — so nothing stalls for lack of a sign-off. | [7 empty] | Guide ↗
Vendor | Workstream | Quote | Approved | Approval status | Deposit | Invoice | Payment | Fees (delivery/rush/install)
Acme Furniture | FF&E | 52000 | 52000 | Approved | Paid | — | Pending | $1,200 delivery
NetWire IT | IT/AV | 14500 | 14500 | Approved | — | Received | Pending | $800 rush
Workspace Co | FF&E | 9800 | — | Awaiting Finance | — | — | — | —
Total |  | 76300 | 66500 |  | 0 | 0 | 0 | 0

## Vendor Contract Tracker
Vendor Contract Tracker | [5 empty] | ← Index
A register of vendor contracts and SOWs — scope, term, key dates, deposit, status — so you know what each vendor owes you and when. | [5 empty] | Guide ↗
Vendor | Scope / SOW | Contract value | Signed? | Key dates | Deposit | Status
ABC Movers | Move day + packing | 18000 | Yes | Move Jun 14 | 50% due Jun 7 | Active
Acme Furniture | Supply + install | 52000 | Yes | Install Jun 16 | Paid | Active
CleanCo | Recurring janitorial | $1,400/mo | No | Start Jun 16 | — | Awaiting signature
Total |  | 70000

## Invoice Checklist
Invoice Checklist |  |  |  | ← Index
A quick check before paying any invoice — matches the quote/PO, work delivered, fees expected, certificate of insurance (COI) current — so you're not paying for what didn't arrive. |  |  |  | Guide ↗
Done | Item | Owner | Due | Notes
☐ | Matches the approved amount in the Purchase Approval Log
☐ | Matches the quote / PO — line items and totals
☐ | Work or goods actually delivered (and accepted)
☐ | Fees are ones you expected — delivery, rush, install; no surprises
☐ | Deposits credited — you're not paying them twice
☐ | Damaged/missing items resolved (Damage & Warranty Log) before final payment
☐ | Certificate of insurance (COI) current, if required for the vendor (COI Tracker)
☐ | Right approver signed off per threshold

## Safety & Compliance
Safety & Compliance Checklist |  |  |  | ← Index
The unglamorous opening basics — certificates of insurance (COIs), life safety, evacuation routes, first aid, accessibility, inspections — confirmed before people arrive. |  |  |  | Guide ↗
Done | Item | Owner | Due | Notes
☐ | Vendor certificates of insurance (COIs) collected and approved (COI Tracker)
☐ | Additional insured language correct
☐ | Building access approvals confirmed

## Emergency Contact Sheet
Emergency Contact Sheet |  |  | ← Index
One sheet of who to call when something goes wrong — building, security, medical, utilities, key vendors — posted where people can find it. |  |  | Guide ↗
Situation | Contact | Phone | Notes
Building emergency | Property manager |  | After-hours line too
Security | Building security desk
Medical emergency | 911 / local |  | Nearest urgent care:
Fire / life safety | Building + local FD
Power / HVAC failure | Building engineering
Plumbing / water | Building / vendor
IT / network down | IT lead
Lock-out / access | Property manager / security

## Final Readiness Walk
Final Readiness Walk |  |  |  | ← Index
The last walk before opening — safety, access, core function, cleanliness — with photos, so you open knowing the space is actually ready. |  |  |  | Guide ↗
Done | Item | Owner | Due | Notes
☐ | Access — sidewalk → lobby → suite → seat works for someone with no instructions
☐ | Power — workstations powered; devices charge
☐ | Connectivity — Wi-Fi up; a real call works in day-one rooms
☐ | Restrooms & kitchen — functional, stocked, clean
☐ | Life safety — exits clear, signage up, extinguishers/alarms in place
☐ | Cleanliness — final clean done; debris and protection removed
☐ | Wayfinding — temporary signage posted
☐ | Issue channel — live and shown to employees
☐ | Photos taken — document the final state (Photo Log)

## Hypercare Tracker
Hypercare Tracker | [6 empty] | ← Index
One issue list for opening week, sorted by urgency, so people can see that someone is watching and fixing the list. | [6 empty] | Guide ↗
# | Reported | Issue | Location | Category | Owner | Next action | Status
1 | 2026-06-22 | Wi-Fi drops in NE corner | Room 4 | Urgent | IT | Add/relocate access point | In progress
2 | 2026-06-22 | Out of paper towels | Kitchen | Opening-week | Office mgr | Restock + adjust reorder | Done
3 | 2026-06-23 | Wants standing desk | Desk 12 | Nice-to-have | FF&E | Add to next order | Open

## Issue Intake Form
Issue Intake Form |  |  |  | ← Index
A simple intake so opening-week issues arrive in one place with what's needed to act — location, problem, reporter, urgency — instead of scattered across channels. |  |  |  | Guide ↗
Done | Item | Owner | Due | Notes
☐ | What's the issue? Plain description
☐ | Where? Room / area / desk
☐ | Reported by + how to reach them
☐ | When noticed
☐ | Urgency (their view): blocking / annoying / minor
☐ | Photo, if helpful

## Week-One Closeout Update
Week-One Closeout Update |  |  |  | ← Index
The end-of-first-week update — what opened, what's resolved, what remains and who owns it — that hands the office off from launch mode to normal operations. |  |  |  | Guide ↗
Done | Item | Owner | Due | Notes
☐ | What opened successfully — the wins, stated plainly
☐ | What was resolved this week — from the Hypercare Tracker
☐ | What remains open — honestly, with owners
☐ | Who owns each remaining item
☐ | What employees should expect next — how to report issues from here, what finish work is coming

## Closeout Binder Checklist
Closeout Binder Checklist |  |  |  | ← Index
Everything future-you needs in one place — floor plan, vendor directory, warranties, manuals, access records, budget archive, lessons learned. |  |  |  | Guide ↗
Done | Item | Owner | Due | Notes
☐ | Final floor plan
☐ | Vendor Directory (with warranty info)
☐ | Warranty information and furniture, fixtures & equipment (FF&E) inventory (FF&E Inventory)
☐ | Equipment manuals
☐ | IT and audio/visual (AV) documentation
☐ | Access records (Access Card Tracker)
☐ | Building rules (Building Rules Summary)
☐ | Emergency contacts
☐ | Recurring service schedule
☐ | Budget / invoice archive
☐ | Lessons learned

## Recurring Ops Calendar
Recurring Operations Calendar |  | ← Index
The schedule that keeps the office running after opening — janitorial, restock, HVAC, pest, plants, walk-throughs — so operations run on a cadence, not on memory. |  | Guide ↗
Task | Cadence | Owner / vendor
Janitorial | Nightly / weekly | Vendor
Pantry & supply restock | Weekly | Reorder cadence owner
Office supplies | As needed / weekly
Facilities issue tracking | Ongoing
HVAC requests / filter changes | Per building
Pest control | Monthly / quarterly
Plants | Weekly / biweekly
Mail / shipping | Daily
Event setup | As needed
Maintenance walk-throughs | Monthly
Vendor performance review | Quarterly

## Vendor Performance Notes
Vendor Performance Notes | [5 empty] | ← Index
A quick record of how each vendor actually performed — on time, on budget, would-rehire — so renewals and the next project start from evidence, not memory. | [5 empty] | Guide ↗
Vendor | Workstream | On time? | On budget? | Quality | Would rehire? | Notes
ABC Movers | Move | Yes | Yes | High | Yes | Great foreman; book early
Acme Furniture | FF&E | Mostly | Yes | High | Yes | One delivery slipped a day
NetWire IT | IT/AV | No | +rush fee | Medium | Maybe | Needed chasing; confirm dates in writing

## Lessons Learned Log
Lessons Learned Log |  |  | ← Index
What worked, what didn't, and what you'd tell the next person — captured while it's fresh, so the next opening (or the next hire) starts smarter. |  |  | Guide ↗
Topic | What happened | What we'd do differently | Keep doing?
Freight elevator | Booked late, nearly lost a day | Reserve in week one, not week three | —
COIs | One vendor's was wrong on move day | Send required language the day we book | Track in one sheet
Daily standup | Caught blockers early | — | Yes, every day

## Great-Office Scorecard
Great-Office Scorecard |  |  |  | ← Index
A ten-minute self-assessment of your office against the six-pillar standard — to find the weakest pillar and your next improvement. |  |  |  | Guide ↗
Pillar | What "great" looks like | Score 1–5 | Biggest gap | Next action / owner
1. It just works | Power, Wi-Fi, rooms, access never fail
2. Feels good to be in | Light, air, acoustics, comfort
3. Fits how you work | Right mix of focus / collab / social
4. Welcomes everyone | Accessible + inclusive by default
5. Shows who you are | Culture made legible; recruiting pitch
6. Stays great | Owned, stocked, maintained, measured

## Space & Ratios Worksheet
Space & Ratios Worksheet |  |  | ← Index
Size the mix — desks, meeting rooms, focus and social space — against your real headcount and in-office pattern, before you lock the layout. |  |  | Guide ↗
Input | Your number | Rule of thumb | Notes
Total headcount |  | —
Typical in-office % (busy day) |  | plan for the peak
Peak people on site |  | headcount × busy-day %
Desks / seats |  | ≥ peak on-site | set a sharing ratio if hybrid
Small rooms (1–4 people) |  | most teams are short here
Medium / large rooms |  | per meeting load
Focus / phone booths |  | ~1 per 8–10 seats
Social / café seats |  | grows with collaboration
Accessible + wellness rooms |  | never "zero" | see Belonging & inclusion

## Workplace Experience Survey
Workplace Experience Survey |  |  |  |  | ← Index
A short, recurring pulse on how the office actually feels to the people in it — across the six pillars. Two minutes to answer, honest signal back. |  |  |  |  | Guide ↗
# | Question | Type | This survey avg | Last survey avg | Δ
1 | The office just works — Wi-Fi, rooms, and access rarely get in my way. | Rate 1–5
2 | It's a comfortable place to be — light, noise, and temperature work for me. | Rate 1–5
3 | I can find the right kind of space for what I need (focus, collaborate, socialize). | Rate 1–5
4 | I can get a meeting room when I need one. | Rate 1–5
5 | The office feels welcoming and inclusive to me. | Rate 1–5
6 | The space feels like us — it reflects who this company is. | Rate 1–5
7 | When something's wrong, I know how to report it and it gets fixed. | Rate 1–5
8 | What's the one thing that would most improve the office for you? | Open
9 | What's working well that we should protect? | Open

## Post-Occupancy Review
Post-Occupancy Review | [5 empty] | ← Index
A structured look back at 30 / 60 / 90 days after opening — what's working, what isn't, and what to fix while impressions are fresh. | [5 empty] | Guide ↗
# | Agenda item | What to bring / look for | Findings | Keep / Fix / Decide | Owner | Date
1 | By the numbers | survey trend, scorecard, top ticket themes.
2 | What's working | name it, so you protect it.
3 | What's not | the recurring complaints and the dead spaces.
4 | Surprises | what we didn't predict (rooms too small, a corner nobody uses).
5 | The six pillars | quick pass: which are strong, which slipped.
6 | Decisions | keep / fix / decide, with owners and dates.

## Quarterly Workplace Review
Quarterly Workplace Review |  |  |  |  | ← Index
The recurring home for "keep it great" — revisit the signals, pick one pillar, ship one improvement. The cadence that stops an office from drifting. |  |  |  |  | Guide ↗
# | Agenda item | Inputs / what to ask | Notes & decision | Owner | Due
1 | Re-score the Great-Office Scorecard | what moved since last quarter?
2 | Survey trend | experience survey deltas and the lowest question.
3 | Usage & tickets | what's crowded, empty, or repeatedly breaking.
4 | Last quarter's actions | did they land? Keep, drop, or extend.
5 | This quarter's pick | the one weak pillar to improve, and the experiment to try.
6 | Owners, dates, budget | and how we'll tell people what changed.

## Day-One Greatness Checklist
Day-One Greatness Checklist |  |  |  | ← Index
Beyond the opening-readiness floor — did we actually open great? A six-pillar check for opening morning, not just "is it safe to use?" |  |  |  | Guide ↗
Done | Item | Owner | Due | Notes
☐ | Wi-Fi, power, rooms, and access all tested live (per Opening Readiness)